FDAC Court Timeline – Positive Route with a Plan for Reunification

| Week | Action |
| --- | --- |
| - Week 5 | Legal planning meeting- Decision made to enter TACS |
| - Week 4 | Joint home visit by TACS & SW – Invite delivered to parents to Pre proceedings meeting (pre-court meeting) |
| - Week 2 | PPM held with parents , lawyers , SW & TACS to confirm agreement in principle to TACS assessment day & hair strand testing instructed to report by week 5 |
| Week 1 – Day 1 Day 2 | Legal Services lodge application form C110A – with: - SW statement - All current assessments, - Chronology - Genogram - Threshold (Legal to prepare) - Allocation proposal (Legal to prepare) - Index of checklist documents (Legal to prepare) - Court issue case - Court considers allocation of case to FDAC - Legal serves application form and evidential documents on the parties - Court makes standard direction that Children’s guardian be appointed and for hair strand testing/joint funding by week 5 - LA starts CPR and identifies all family members/starts stage 1 & 2 viability assessments if not already done so and book adoption medical. - Kinship schedule updated |
| 3 (by day 12 or first available FDAC) | Introductory FDAC Hearing – Court to give directions for the filing of stage 2 viability assessments by week 5 and the TACS’ initial assessment report by week 5 |
| 5 | CMH - Parents sign agreement with TACS at Court and agree intervention plan. - Court to give detailed case management directions – - instruct any outstanding assessments, including hair strand testing by week 16. - order adoption medical if no ICO. - Fully timetable and list for IRH-timetable case for positive outcome. - Stage 2 Viability assessments of extended family completed by C&F workers. - If the initial assessment report recommends FDAC, case transfers to TACS. If not recommending FDAC and Judge agrees, case remains with C&F team and all tasks responsibility of C&F worker thereafter – case proceeds in conventional court. - Stage 3 full kinship assessments commenced Non-Lawyer reviews weeks 7,13,15,19,21,23 & 27 |
| 10 | Interim TACS report to be discussed and agreed by TACS, C&F SW and legal – email exchange. Liberty to convene care plan meeting if necessary. |
| 11 (wk 6 from CMH/2nd hearing) | Interim TACS report filed and served on Wednesday prior to FDAC Lawyer review (If Interim report is negative – court to consider transferring to conventional court and follow that timeline). Case transfers to C&F SW team. |
| 16 | TACS substantive report to be discussed and agreed by TACS, C&F SW and legal – email exchange. Liberty to convene care plan meeting if necessary. |
| 17 (wk 12 from CMH/2nd hearing) | Substantive TACS report/Kinship stage 3 assessments filed (by Wed prior to FDAC) Lawyer Review – Court to consider whether timetable needs to be extended beyond week 33 |
| 23 | - Convene final care plan meeting - consider ADM if plan changes to negative/adoption route - draft final TACS assessment to be available - balance sheet completed as part of final care plan - Final SWET not required in TACS |
| 25 | LA File and Serve Final evidence and care plans including Final TACS Assessment Lawyer Review Can be vacated if all parties agree to TACS final evidence & care plan |
| 27 | Parents’ final evidence filed |
| 29 | Guardian’s final evidence filed Advocates meeting / LA case summary |
| 31 | IRH/Case management order or finalise if possible |
| 33 | FH (Only if necessary) |